## Fire CP
|  |  |  | January |  |  |  |  | February |  |  |  | March | [17 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July
DA Ref | Task | File Ref | Responsible Officer | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 6 | 13 | 20 | 27 | 3 | Date Completed | Checked By
| Compliance Review - SORP / BVACOP |  |  | April 10: B a n k H o l i d a y; April 13: B a n k H o l i d a y; May 4: B a n k H o l i d a y; May 25: B a n k H o l i d a y; June 18: S u b m i s s i o n f o r C a b i n e t A g e n d a D e a d l i n e; June 25: S t a t u t o r y D e a d l i n e
Prepare and issue year end instructions | bar: March 2; April 4; April 10 to April 11; April 13; April 18; April 25
Prepare and process Admin Account | bar: February 23 to March 29; April 4; April 10 to April 11; April 13; April 18; April 25
Processing of Depreciation and Revaluations | bar: February 2; April 1 to April 4; April 6 to April 11; April 13 to April 18; April 20 to April 25; April 27 to April 30
Final closedown timetable issued | bar: March 2; April 4; April 10 to April 11; April 13; April 18; April 25
Review and agree treatment of Financial Instruments | bar: April 1 to April 4; April 6 to April 11; April 13 to April 18; April 20 to April 25; April 27 to May 10
Stock levels | bar: April 1 to April 4; April 6 to April 11; April 13; April 18; April 25
Capital accounts closed | bar: April 1 to April 4; April 6 to April 11; April 13 to April 18; April 20 to April 25; April 27 to April 30
Feeder deadlines | bar: April 4; April 10 to April 11; April 13; April 18; April 25
Final movement in ledger (Accountancy) | bar: April 1 to April 4; April 6 to April 11; April 13 to April 18; April 20 to April 25; April 27 to May 10
Committee - Summary of Provisional Outturn Report | bar: April 4; April 10 to April 11; April 13; April 18; April 25; May 28
Information from 3rd Parties | bar: April 1 to April 4; April 6 to April 11; April 13 to April 18; April 20 to April 25; April 27 to June 7
FRS 17 - GAD report / LGPS Produce Entries | bar: April 4; April 10 to April 11; April 13; April 18; April 25; May 23 to May 27
Produce I&E account / Movement in General Fund statement | bar: April 4; April 10 to April 11; April 13; April 18; April 25; May 9 to May 17; May 28
Produce balance sheet | bar: April 4; April 10 to April 11; April 13; April 18; April 25; May 9 to May 12; May 29 to May 31
Produce all supporting notes to SOA | bar: April 1 to April 4; April 6 to April 11; April 13 to April 18; April 20 to April 25; April 27 to June 7
Produce STRGL | bar: April 4; April 10 to April 11; April 13; April 18; April 25; May 16 to May 19; May 30 to June 1
Cash Flow Statement | bar: April 4; April 10 to April 11; April 13; April 18; April 25; May 20 to May 25; June 2
Produce Pension Fund Account & Notes | bar: April 4; April 10 to April 11; April 13; April 18; April 25; May 23 to May 27; June 2
1st draft to DFIT / ADFS / DFTS to approve | bar: April 4; April 10 to April 11; April 13; April 18; April 25; June 5 to June 9
Final draft proofed and signed off | bar: April 4; April 10 to April 11; April 13; April 18; April 25; June 10 to June 16
Submission of final report to committee section | bar: April 4; April 10 to April 11; April 13; April 18; April 25; June 17 to June 18
Analytical Review | bar: April 1 to April 4; April 6 to April 11; April 13 to April 18; April 20 to April 25; April 27 to June 7
Final Report to Committee 24/06/09 | bar: April 4; April 10 to April 11; April 13; April 18; April 25
Fortnightly Meetings with GMFRA | bar: April 4; April 9 to April 11; April 13; April 18; April 23; April 25; May 7; May 21; June 4; July 20 to July 27
Previous Dates