## Timetable
GMFRA CLOSEDOWN TIMETABLE – CONSOLIDATION OF ACCOUNTS 2009/10
Ref | Target |  | Responsible | Date
| Date | Task |  | Achieved | Comments | Days
September - Faster Closing Plan
| Sept | Bring forward 2008/09 balances | JH | 2009-10-21
| Sept | Balance sheet monitoring Aug 09 / suspense/control accounts update position | JH | 2009-09-25
October - Faster Closing Plan
| Oct | Balance sheet monitoring Sept 09 / suspense/control accounts update position | JH | 2009-10-13
| Oct | Review SORP 2009 Changes and Action Plan | AG/JS/TC
November - Faster Closing Plan
| Nov | Update existing Statement of Accounts | AG | 2009-11-04
| Nov | Review Working Papers and Sharepoint - share with External Audit | AG/JH
| Nov | Identify problem areas in 2008/09 closedown requiring preventative attention | AG | 2009-11-12
| Nov | Balance sheet monitoring Oct 09 / suspense/control accounts update position | JH | 2009-11-11
| Nov | Review any LAAP changes | AG
| Nov | Review ISA 260 items and agree changes | AG/TC
| Nov | Review Accounts and Audit Regulations 2006 | JS/AG
| Nov | Budget Monitoring Report Q2 | AG/TC | 2009-10-28
December - Faster Closing Plan
| Dec | Review any additional items on External Audit Management letter/ Regularity Report | AG
| Dec | Review of Returns for Pensions Data (GAD) by 31/12/09 | AG
| Dec | Review Major Reconciliation areas - Admin Committee. Also Control Accounts and Recharge Process | AG
| Dec | Review any extra WGA requirements | AG/JS
| Dec | Identify best practice SOA with other authorities | AB
| Dec | Review and agree Accounting Policies - Capital and Revenue | AG
| Dec | Balance sheet monitoring Nov 09 / suspense/control accounts update position | JH | 2009-12-09
January - Faster Closing Plan
| Jan | Produce Final Accounts Manual | JS/AG
| Jan | Risk Register and Critical Path Analysis/ Gaant Chart | AG | 2009-11-12
| Jan | Review of SORP detailed guidance - (only available Dec) | AG/JS
| Jan | Balance sheet monitoring Dec 09 / suspense/control accounts update position | JH | 2010-02-08
| Jan | Revaluation and depreciation completed – entries processed in Asset Register | DS/AB |  | delayed to be completed in March/ early April due to Fixed Asset Upgrade Project
| Jan | Budget Monitoring Q3 | AG/TC | 2010-01-18
February - Faster Closing Plan
| Feb | Plan resource time, ensure resource available , prepare responsibility statement | TC
| Feb | Preparatory meeting with DA, Preliminary meeting with Fire | AT/TC/AE/DS
| Feb | Review previous years process and check progress on audit plan recommendations | AT/TC
| Feb | Balance sheet monitoring Jan 10 / suspense/control accounts update position | JH
| Feb | Provide GAD with completed data collection spreadsheet | JHi |  | Submission of information delayed until 22nd February.
March - Faster Closing Plan
| Mar | Review – Agresso Period end February processing note – period in balance | AE/JH
| Mar | Accounting Polices Review – Capital and Revenue | AG
| Mar | Progress meeting with Fire | TC/AG/DS/AE
| Mar | Issue instructions and year-end deadlines/guidance to Fire users | TC/JS/AG
| Mar | Balance sheet monitoring Feb 10 / suspense/control accounts update position | JH
| Mar | Admin Account allocated and Charges processed | AE/DS
| Mar | Capital
|  | Establish Minimum Revenue Provision and VRP calculation | AG
| Mar | Closedown Items | AE/AH
|  | Request details of stock levels as at 31st March | DB
|  | Review Insurance Fund Charged in year | AG
|  | GAD to review data and raise queries by 25/03/10 | JHi
| Mar | Compliance
| Mar | Issue Working Paper Requirements and set up folders in Sharepoint | AG/JH
| Mar | Agree process regarding 3rd Parties External – Accounts | AG
| Mar | Issue Declaration of interest to Members | JH
| Mar | Identify requirements for notes to the accounts | AG
| Mar | List of Responsibilities Issued | TC
April
| Apr | Review - Agresso Period end Mar processing note (period in balance) | AE/JH
| Apr | Balance sheet monitoring Mar 10 suspense/control accounts update position | JH
| Apr | Final deadline creditor/debtor lists, stock returns | DS/AE
BANK HOLIDAY - 2nd and 5th April
| Apr | Capital
|  | Prepare list of capital accruals | AE
|  | Prepare Capital Outturn Report | JC
|  | Agree total capital programme | JC
|  | Asset register purchases and disposals completed | DS
|  | Complete Impairment review | DS
|  | Establish available cap receipts | AB
| Apr | Identify any Group Accounts | AE/DS
| Apr | Review progress meeting with Fire | TC/DS/AE/AG
| Apr | Closedown items
|  | Agree interest with G Parkinson | AG
|  | Debtor/creditor lists received from departments | GMFRA
|  | Undertake/Validate stock & submit information to Finance Department | GMFRA
|  | Insurance vehicle accident costs to be agreed with Fire | AG
|  | Provide GAD with Cash flows and membership summary | AE
|  | Agree VAT Debtor | AG
|  | PFI - identify figures to be included on Balance Sheet | AG/JM/ PS
|  | Journals (on line input) – Fire | GMFRA
|  | Identify any work in progress | GMFRA
|  | Final old year period 13 items agreed | All
| Apr | Outturn position on Pension Fund | TC/AE/AG
May
| May | Review - Agresso Period end April processing note (period in balance) | AE/JH
| May | Final deadline for old year Journals/Confirm all entries in the GL
BANK HOLIDAY - 3rd May
| May | Balance sheet monitoring April 10 / suspense/control accounts update position | JH
| 14th May | GAD Report issued | AG
| May | Meeting with GMFRA | TC/DS/AE/AG
| May | Returns | AG
| May | Closedown Items
|  | Finalise Insurance Fund | AG
|  | Finalise position on Pension Funds (including FRS17) and Pension Fund Account | TC/AG
|  | Complete CAA | AG
|  | Government Grants – final position including debtors/creditors | AG
| May | Outturn Report
|  | Prepare first draft Outturn report | TC
|  | Outturn report sent to GMFRA | TC
|  | Outturn reports to F&GP May 20th | TC
| May | Consolidation work
|  | Explanatory Foreword – Member/DFIT | AG
|  | Capital – Capital a/cs and statements completed | DS/AB
|  | Sign off FRS17 notes to the accounts | TC
|  | Produce I&E in BV format and Statement of Movement on the GF Balance | AG
|  | Produce Statement of Total Recognised gains and losses | AG
|  | Analyse reserves and provisions | AG
|  | Produce final CBS | AG
|  | Produce Cashflow statement | AG
|  | Produce Pension Fund Account | AE/AG
|  | Produce final revenue notes to I&E and CBS | AG
|  | Produce final capital notes to I&E and CBS | AG
| May | Sign off final capital notes to I&E and CBS | TC
|  | Sign off final revenue notes to I&E and CBS | TC
|  | Produce 1st Draft of Accounts to HOFD | AG
|  | Analytical Review of full SOA | TC
|  | Meet with Fire - finalise draft statement of accounts | TC
|  | Final Draft of statement of accounts to Exec Director BSS | AG
|  | Final pre-Audit set of accounts proof read and additions checked | AG
|  | Arrange with GMFRA to obtain Signatures at F&GP meeting | JH
|  | Statement of Accounts to GMFRA for meeting | AG
BANK HOLIDAY - 31st May
June
| Jun | Review - Agresso Period end May processing note (period in balance) | AG
| Jun | Review progress meeting with Fire | TC/AH/AE/AG
| Jun | Balance sheet monitoring May 10/ suspense/control accounts update position | JH
| Jun | Returns
|  | CIPFA Fire Statistics/Capital Outturn forms completed | JC
|  | Revenue Outturn forms | AG
| 23rd Jun | Report to Audit Committee (Confirm date and committee) | TC
July – POST SOA REPORTED
| Jul-Sept | Compliance
|  | Ensure all working papers are available and on Sharepoint and meet with DA requirements | AG/JH
|  | Audit of Accounts - Liase with External Audit | All
Period of Public Inspection
Presentation of SAS610 (If Applicable)
|  | Advert for completion of Audit | AG
|  | Arrange for printing / produce by 30 September | AG/JH